## Estimation
Project Title: Twinkle Star Dance Technology: PHP & MySQL Framework: Yii Browser Compatibility: IE8 and above and latest version of firefox, chrome and safari
# | Tasks |  | Comments & Assumptions | Week - 1 | Week - 2 | Week - 3 | Week - 4 | Week - 5 | Week - 6
Total
1 | Designing database and project setup
| Detailed Requirements Gathering, Understanding, Database connectivity, Database designing | 30
2 | Static Content
| Static pages like Home, contact us and Managing from backend, Contact Us | 24 | Static pages content can be managed from backend
3 | Authentication
| Login, Logout, Change Password, Forgot Password | 24 | by different users ie admin, dancers, instructors, studios
| Admin Settings | 12
4 | Video Management
| Manage individual videos ie Add, Edit, View, Delete | 24 | Videos can be added, deleted with a price. Video details page will allow admin to add video to a subscription or remove that video from a subscription.
5 | Package Management
| Manage Package ie Add, Edit, View, Delete | 20 | Package will have one or more subsciptions. Package cost will be decided based on summation of subscription cost with an extra parameter of discount which will affect total cost.
6 | Subscription Management
| Manage Subscription | 20
7 | Studio Management
| Registration | 12 | Studio will be registered/Account-created during payment procedure of selected subscriptions/packages
| Manage studio/profile | 12 | Studio can edit its information, password etc
| Instructor Management | 16 | Instructor will be added/deleted by studio, Instructor can manage his profile and change password
| Manage Subscription | 24
| Order Management | 36 | Sees the order that studio has done to subscriptions or packages
| Payment Integration | 32 | Direct Payment without going to paypal site using credit card, payment by paypal user.
| Manage Classes | 28 | Add/Edit/Delete classes by studio.
8 | Dancer Management
| Registration | 16 | Dancer will be registered/Account-Created during payment procedure of videos
| Manage dancer/profile | 12
| Order Management | 18 | Sees the order that dancer has done to videos/classes.
| Payment Integration | 16 | Direct Payment without going to paypal site using credit card, payment by paypal user.
9 | Email Management
| Email subscription | 20 | Email templates can be managed from backend.
10 | Data Migration | 80 | Existing data migration into the new database
| Total Development Hours | 476
| Design Development & Integration | 66
| QA | 56
| Total | 598